## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | BC; 10/6 | Pass | BC; 11/1 | Pass | BC; 11/23
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | BC; 10/6 | Pass | BC; 11/1 | Pass | BC; 11/23
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | GM; 10/6 | Pass | GM; 11/1 | Pass | GM; 11/23
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | KS; 10/6 | Pass | KS; 10/31 | Pass | KS; 11/23
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | KC; 10/6 | Pass | KC; 10/31 | Pass | KC; 11/23
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | KC; 10/6 | Pass | KC; 10/31 | Pass | KC; 11/23
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | JP; 10/6 | Pass | JP; 11/1 | Pass | JP; 11/23
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | JP; 10/9 | Pass | JP; 11/1 | Pass | JP; 11/23
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | JP; 10/9 | Pass | JP; 11/1 | Pass | JP; 11/23
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | KC; 10/9 | Pass | KC; 11/1 | Pass | KC
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | KC; 10/9 | Pass | KC; 11/1 | Pass | KC; 11/23
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | GM; 10/9 | Pass | GM; 11/1 | Pass | GM; 11/23
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | GM; 10/9 | Pass | GM; 11/1 | Pass | GM; 11/23
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | BC; 10/9 | Pass | BC; 11/1 | Pass | BC; 11/23
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | KS; 10/9 | Pass | KS; 11/1 | Pass | KS; 11/23
As a Player I want to Resign the Game so that I can do something else. | Given that I am playing a game when I press the resign button then I expect the game to end with my opponent winning |  |  | Pass | KS; 11/1 | Pass | KS; 11/23
| Given that I am playing a game when my opponent resigns then I expect the game to end with me winning |  |  | Pass | KS; 11/1 | Pass | KS; 11/23
As a Player I want to change my last move so that I can make a new move. | Given that its my turn, when the turn has not ended, then I can backup my current move |  |  | Pass | BC;11/1 | Pass | BC; 11/23
| Given That its my turn when the move has not started, then I cannot start a backup |  |  | Pass | BC;11/1 | Pass | BC; 11/23
| Given that its my turn when the turn has been submitted, then I cannot backup my move |  |  | Pass | BC;11/1 | Pass | BC; 11/23
| Given that its my turn when I have not made any moves, then I cannot backup my move |  |  | Pass | BC;11/1 | Pass | BC; 11/23
| Given that its my turn when I start my turn then the backup move button can be pressed |  |  | Pass | BC;11/1 | Pass | BC; 11/23
As a player I want to send my turn so that the other player gets it. | Given that its my turn when the move has been validated, then I can submit my move |  |  | Pass | JP; 11/1 | Pass | JP; 11/23
| Given that its my turn when a valid move is made and the turn is complete , then I can submit the move |  |  | Pass | JP; 11/1 | Pass | JP; 11/23
| Given that its my turn when the submit button is pressed, then the move is submitted |  |  | Pass | JP; 11/1 | Pass | JP; 11/23
| Given that its my turn when the game is in the Stable Turn state, then the submit button is enabled |  |  | Pass | JP; 11/1 | Pass | JP; 11/23
As a player I want to sign out so that I can not play a game of checkers. | Given I am logged in when I select the option to log out then I will be logged out. |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
| Given I log out when I am on the website then I will be redirected to the home page. |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
As a Player I want my moves to be validated so that I follow the rules. | given that its my turn when I can take a piece and I choose to take the piece, then the piece is taken |  |  | Pass | KC;11/1 | Pass | KC; 11/23
| Given that its my turn when a piece is taken, then the turn continues if another capture is possible with that same piece |  |  | Pass | KC;11/1 | Pass | KC; 11/23
| Given that its my turn when a move takes the piece to the end of my opponent's side of the board, then the piece is kinged |  |  | Pass | KC; 11/1 | Pass | KC; 11/23
| Given that its my turn when a piece is taken, then the turn ends if another capture is not possible with that piece |  |  | Pass | KC; 11/1 | Pass | KC; 11/23
| Given that its my turn when i make a simple move when none of my pieces can make a jump then the move is valid. |  |  | Pass | KC;11/1 | Pass | KC; 11/23
As a Player I want to Win/Lose so that I can play another game. | Given that I am currently playing a game when I resign a game then I expect to lose the game |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
| Given that I am currently playing a game when my opponent resigns a game then I expect to win the game |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
| Given that I am currently playing a game when my opponent can make no more moves then I expect to win the game |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
| Given that I am currently playing a game when I can make no more moves then I expect to lose the game |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
| Given that I am currently in the Game View when the game ends then I expect to be informed of my result |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
| Given that I am currently in the Game View when the game ends then I expect to be able to return to the Home Page |  |  | Pass | GM; 11/1 | Pass | GM; 11/23
As a Player I want to Check if it's my turn so that I can make my move. | Given I am playing a game when I check turn then I see if it's my turn. |  |  | Pass | KS;11/1 | Pass | KS; 11/23
As a player I want to record the moves of a game so that I can watch a replay of the game later | Given a player starts a game When a game starts then record the player names to the replay class |  |  |  |  | Pass | KS; 11/23
| Given a move is made by either player when a game is being played then it is recorded into a replay file. |  |  |  |  | Pass | KS; 11/23
| Given a game is in progress when the game ends then the replay file is saved |  |  |  |  | Pass | KS; 11/23
| Given a game is in progress when a player resigns then the resignation is recorded to the replay file |  |  |  |  | Pass | KS; 11/23
As a player I want to watch a game replay so that I can see how the game was played. | Given a previous game has been stored into a replay file when I select it to be replayed then the site will play out each move in sequence on a board. |  |  |  |  | Pass | KC; 11/23
| Given I want to skip ahead or behind _n_ amounts of moves when I press the control to scrub then the replay will move the game ahead or behind that amount of moves |  |  |  |  | Pass | KC; 11/23
| Given I want to pause when I press the pause button then the replay will stop playing until unpaused. |  |  |  |  | Pass | KC; 11/23
As a game I want to display all the possible moves so that I can help the player. | Given a game is in session, when a player selects the help button and the game has recorded the possible moves then the board will highlight all the pieces that the user can move. |  |  |  |  | Pass | GM; 11/23
| Given that a game is in session, when the user selects the help button then a help dialog is displayed with an instruction manual |  |  |  |  | Pass | GM; 11/23
As a game I want to calculate all the possible moves so that I can help the player. | Given a game is in session, when a player selects the help button then the game will calculate all the possible moves for that player. |  |  |  |  | Pass | JP; 11/23
| Given that a game is in session, when the player selects a piece then the possible moves for that piece are highlighted. |  |  |  |  | Pass | JP; 11/23